## Project Priority Matrix
| Constrain | Enhance | Accept
Scope
Time
Budget

## Risk Scoring Template
Defined Conditions for Risk Management Analysis
Project Objective | Relative or Numerical Scales
| Very Low - 1 | Low - 2 | Moderate - 3 | High - 4 | Very High - 5
Time | Insignificant Schedule Slippage | Schedule Slippage <5% | Schedule Slippage <5 -10% | Schedule Slippage <10 - 15% | Schedule Slippage > 15%
Scope | Scope Decrease Barely Noticable | Minor Areas of Scope Affected | Major Areas of Scope Affected | Scope Reduction Unacceptable | Scope reduction results in unfinished game
Quality | Quality Degradation Barely Noticeable | Only Very Demanding Features Are Affected | Quality Reduction Requires Team Approval | Quality Reduction Unacceptable | Project Item is Effectively Unplayable

## Risk Mgmt Analysis Template
Risk Management Analysis TEMPLATE
RISK EVALUATION
Risk | Probability | Time | Scope | Quality | Risk Score
Schedule Flaws | 40% | 3 | 2 | 2 | 2.8
Poor Productivity | 30% | 3 | 3 | 3 | 2.7
Data Loss | 25% | 3 | 2 | 3 | 2
Delayed Assets | 25% | 2 | 1 | 4 | 1.75
Android Required Language Change | 15% | 5 | 1 | 5 | 1.65
Scope Creep | 15% | 3 | 4 | 3 | 1.5
Team Reduction | 5% | 5 | 4 | 4 | 0.65
Hardware Failure | 10% | 2 | 1 | 1 | 0.4
Licensing Conflict | 5% | 5 | 1 | 2 | 0.4
Repository Failure | 5% | 3 | 1 | 1 | 0.25
NOTE: This form will suffice for showing the RISKS, the Risk Scores and the Order of Risks…

## Risk Response Template
Risk Response Matrix
Risk Event | Response* | Contingency Plan | Trigger | Person Responsible
Schedule Flaws | Mitigate | Reschedule Tasks, and Reallocate Resources | Many Tasks are farm from planned deadline | Vince
Poor Productivity | Mitigate | Team meeting to address issues | No progress updates between scheduled meeting | Jordon
Data Loss | Eliminate | Each team member has multiple backups of repository | Loss of Data | Individuals that applys
Delayed Assets | Mitigate | Create filler art with basic primitives | Missed deadlines by artists | Derek
Android Required Language Change | Accept | Find new engine, and port over to new language | Google changes the infrastructure of the Android Platform | Whole Team
Scope Creep | Mitigate | Schedule more meetings, and make cut backs | Features being added that are not in the original scope definition | Jordon
Team Reduction | Accept | Reallocate Tasks to remaining team members | Loss of a Team member | Jordon
Hardware Failure | Eliminate | Find/buy new primary workstation | Computer crashes | Individuals that applys
Licensing Conflict | Accept | Pay for license/ Job project | Android/AndEngine License becomes out of budget | Whole Team
Repository Failure | Eliminate | Find new repository middleware, and upload all current work | GitHub fails | Derek
* = Eliminate, Mitigate, Share, Transfer, Accept